## List
StevensLive
User Stories (Initial)
DATE | ITEM | STATUS | NOTES OR ANY ISSUE
2017-02-05 | Login screen | NOT STARTED
2017-02-08 | Chat Screen | NOT STARTED
2017-02-12 | Add audio recorder and response | NOT STARTED
2017-02-15 | Design add event screen | NOT STARTED
2017-02-19 | User profile and side menu | NOT STARTED
2017-02-22 | Settings screen | NOT STARTED
2017-02-25 | Event cell design and its information | NOT STARTED
| Check api.ai working | NOT STARTED
| Webservice integration | NOT STARTED
| Stevens login manage | NOT STARTED