## Sprint 1
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Finish login screen functionality (ios) |  | Akshay | Done
2 | Design Filter Screen (ios) |  | Akshay | Done
3 | Design Side menu (ios) |  | Akshay | Done
4 | Design Voice assistant Screen (ios) |  | Akshay | Done
5 | Finish login screen functionality (android) |  | Sonali | Done
6 | Design Filter Screen (android) |  | Sonali | Done
7 | Finish registration screen functionality(android) |  | Celeste | Done
8 | Finish event full description page (android) |  | Celeste | Done
9 | Design the db |  | Pranay, Prateek | Done
10 | Create the db |  | Pranay, Prateek | Done
11 | Create db tables |  | Pranay, Prateek | Done
12 | Get events title from stevens.edu |  | Maha, Rafif | Done
13 | Get events time from stevens.edu |  | Maha, Rafif | Done
14 | Get events category from stevens.edu |  | Maha, Rafif | Done
15 | Get events location from stevens.edu |  | Maha, Rafif | Done
16 | Get events date from stevens.edu |  | Maha, Rafif | Done
17 | Get events description from stevens.edu |  | Maha, Rafif | Done
18 | Fill the db tables with input data |  | Pranay, Prateek | Done
19 | Create API for login and registration |  | Pranay, Prateek | Done
Note: If anyone have trouble or problem then you can ask me.
Note on D10: +ptyagi1@stevens.edu +pbure@stevens.edu Database maha and rafif are creating. You need to start work on api for fetching data from database and create methods so that application can get data from server. _Assigned to Prateek Tyagi_ -Akshay Sunderwani

## Sprint 2
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Handle web scraping exceptions - connection |  | Rafif | Done
2 | fetch categories |  | Maha | Done
3 | fetch full description |  | Maha, Akshay,Rafif | Done
4 | Handle db exceptions - connection |  | Maha,pranay | Done
5 | Handle db exceptions - data type |  | Maha,Rafif | Done
6 | Handle db exceptions - empty list |  | Maha | Done
7 | Handle db exceptions - add only new events |  | Maha | Done
8 | Fill db - category table |  | Maha | Done
9 | Fill db - event category table |  | Rafif | Done
10 | Fill db - event table |  | Maha | Done
11 | Fill - last updated table |  | Maha, Rafif | Done
12 | Setup web server |  | Akshay | Done
13 | Finish design part and start work on api (ios) |  | Akshay | Done
14 | Fill database with events data |  | Pranay, Prateek | Done

## Sprint 3
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Integrate api functionality in ios application |  | Akshay |  | Login, Registration and forgot password done.
2 | Start work on CMS design |  | Maha, Rafif
3 | Create and finish api methods |  | Pranay, Sonali |  | Login, Registration and forgot password done.
4 | Create a web ui to test api |  | Pranay, Prateek
5 | Create log file for api request and response |  | Pranay, Prateek
6 | My feed Screen logic |  | Sonali
7 | My Subscription logic |  | Sonali
8 | Cron job - add new events and delete past event |  | Maha, Rafif, Akshay | working
9
10
11
12
13
14
15
16
17
18
19
20
21