## Sprint 1
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Finish login screen functionality (ios) |  | Akshay | Done
2 | Design Filter Screen (ios) |  | Akshay | Done
3 | Design Side menu (ios) |  | Akshay | Done
4 | Design Voice assistant Screen (ios) |  | Akshay | Done
5 | Finish login screen functionality (android) |  | Sonali | Working
6 | Design Filter Screen (android) |  | Sonali
7 | Finish registration screen functionality(android) |  | Celeste
8 | Finish event full description page (android) |  | Celeste
9 | Design the db |  | Pranay, Prateek | Working
10 | Create the db |  | Pranay, Prateek | Done
11 | Create db tables |  | Pranay, Prateek | Done
12 | Get events title from stevens.edu |  | Maha, Rafif | Done
13 | Get events time from stevens.edu |  | Maha, Rafif | Done
14 | Get events category from stevens.edu |  | Maha, Rafif | Done
15 | Get events location from stevens.edu |  | Maha, Rafif | Done
16 | Get events date from stevens.edu |  | Maha, Rafif | Working
17 | Get events description from stevens.edu |  | Maha, Rafif | Done
18 | Fill the db tables with input data |  | Pranay, Prateek | Done
19 | Create API for login and registration |  | Pranay, Prateek | Working
Note: If anyone have trouble or problem then you can ask me.
Note on D10: +ptyagi1@stevens.edu +pbure@stevens.edu Database maha and rafif are creating. You need to start work on api for fetching data from database and create methods so that application can get data from server. _Assigned to Prateek Tyagi_ -Akshay Sunderwani

## Sprint 2
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Handle web scraping exceptions |  | Maha,Rafif
2 | Handle db exceptions |  | Maha,pranay
3 | Setup web server
4 | Finish design part and start work on api (ios) |  | Akshay
5 | Fill database with events data
6 | Create and finish api methods
7 | Create a web ui to test api
8 | Create log file for api request and response
9 | Scrap events data for local hoboken events
10 | Design android |  |  |  | Sonali, celeste divide this task from your mutual understanding and break it down.